AI Infrastructure & Regional Electricity Demand

A Forecasting Framework for U.S. Grid Stress

Alan Lamb  |  Lambcast Applied Economics  |  M.S. Applied Economics, University of Maryland  |  2026

Master Project Document  —  Version 4.0  |  Updated March 2026

Design Note (v4, March 2026): Original design called for a difference-in-differences causal identification using load-side interconnection queue filings as the treatment variable. Research confirmed that project-level large load queue data does not exist as a public downloadable dataset for any of the three target markets (PJM, ERCOT, MISO). The design has been revised to a forecasting paper with causal motivation. The data gap itself is documented as a policy finding. All pipeline, modeling, and dashboard work proceeds as planned.

# Executive Summary

This project quantifies the relationship between data center investment and regional electricity demand growth, then builds a forward-looking grid stress forecast for three major U.S. electricity markets: PJM (Mid-Atlantic/Midwest), ERCOT (Texas), and MISO (Southeast/Midwest).

The paper combines rigorous descriptive analysis with a production-grade forecasting pipeline. It documents — as an explicit research finding — that causal identification of the data center demand effect is not currently possible with public data, explains what data would be required, and argues this gap represents a significant policy problem. The forecasting model then uses the best available proxy data (generation interconnection queues) to project regional grid stress from the existing investment pipeline.

The project serves two audiences simultaneously. For Amazon Applied Science and industry hiring teams, it demonstrates end-to-end ownership of a production-style data pipeline. For research-oriented teams, it demonstrates research-grade thinking, honest identification of the limits of available data, and a rigorous forecasting methodology. The combination is rare at the graduate student level.

# Core Research Question

How much has data center investment driven regional electricity demand growth — and can we build a model that forecasts future grid stress from the existing investment pipeline?

# What This Paper Claims and Does Not Claim

## Claims

- Data center investment is a primary driver of electricity demand growth in PJM, ERCOT, and MISO

- The generation interconnection queue is a measurable leading indicator of future grid stress

- A forecasting model using queue data, weather controls, and regional economic indicators can project regional demand growth with quantifiable uncertainty

- Causal identification of the per-facility demand effect requires project-level load data that does not currently exist in public form

## Does Not Claim

- A precise causal estimate of MW demand per data center (data does not support this)

- That the generation queue directly measures data center load (it does not — this is an acknowledged proxy)

- Findings that generalize beyond the three target markets

# Key Early Findings (Phase 1 — March 2026)

The following descriptive findings have been established from the EIA and LBNL queue data and are committed to the GitHub repository as charts:

- ERCOT demand grew approximately 27% from 2019 to 2025 on an indexed basis (2019 = 100), while PJM and MISO remained essentially flat at roughly 102–105 by 2025. This divergence is the core visual story of the paper.

- ERCOT interconnection queue filings reached 97 GW in 2024 and 93 GW in 2023 — the two largest years on record by a significant margin. Total ERCOT filings 2019–2024: 403 GW.

- Battery storage emerged as the dominant new generation type in ERCOT from 2022 onward, reflecting grid response to the reliability demands of data center load.

- MISO shows an anomalous 185 GW spike in 2022 driven by queue reform backlog processing — annotated in the chart and documented here to avoid misreading as a demand signal.

- The 50% withdrawal rate in the LBNL queue data (8,058 of 16,156 target-region records) is normal for interconnection queues and does not undermine the forecasting signal — filing volume and trajectory are the relevant variables.

# Output Goals

## Primary: NBER-Style Working Paper

A research-grade working paper posted as PDF on lambcast.net and submitted to SSRN for a permanent citable URL. Target length 25–35 pages. Structure: Abstract, Introduction, Related Literature, Data, The Data Gap, Descriptive Analysis, Forecasting Model, Results, Conclusion, References.

## Secondary: Hex Dashboard

An interactive regional grid stress forecast dashboard showing projections by balancing authority, incorporating the current investment pipeline as forward-looking demand. Primary Amazon Applied Science signal.

## Supporting: Lambcast Blog Posts (5 Posts)

Five public posts on lambcast.net documenting the build process. Not summaries of the paper — the story of constructing it.

# Dual Audience Design

## Amazon Applied Science Signal

- End-to-end pipeline: raw API ingestion through dashboard

- Distributed computing with PySpark for 100M+ row dataset

- Cloud warehouse querying via BigQuery

- Forecasting models: XGBoost, Prophet, ARIMA — benchmarked against each other

- Hex dashboard for interactive regional visualization

- Python + SQL as primary implementation languages

## Anthropic / Research Economist Signal

- Honest documentation of identification limits — a mark of research sophistication

- Explicit data gap analysis as a policy contribution

- Research-grade working paper formatted for SSRN submission

- Related literature section positioning paper within energy economics

- Rigorous forecasting methodology with uncertainty quantification

# Data Audit — Confirmed Sources

| Dataset | Status | Notes |
| --- | --- | --- |
| EIA Form 930 | ✅ IN HAND | 184,102 rows. Hourly demand for PJM, ERCO, MISO, 2019–2025. Saved to data/eia_demand_2018_2025.csv. Core outcome variable. Data type filtered to 'D' (Demand). |
| UMD PJM Queue 2008–2024 | ✅ IN HAND | 7,492 rows, 121 columns. NSF-funded. Generation-side (not load-side). Extends to 2024 (beyond original 2020 estimate). Saved to data/pjm_main_data_for_public_with_additional_vars.csv. |
| LBL Queued Up 2024 | ✅ IN HAND | 36,441 rows, 31 columns, 39 tabs. All-ISO generation queue data. Extracted tab '03. Complete Queue Data' to data/lbnl_queue_data.csv. 16,156 rows after filtering to PJM/MISO/ERCOT. |
| NOAA Weather | ✅ CONFIRMED | NCEI Climate Data Online API. Daily temperature and degree-days by station. Free API key. Key control variable. Not yet pulled. |
| BEA Regional GDP | ✅ CONFIRMED | BEA regional economic accounts. Annual GDP by metro area. Free download. Economic control variable. Not yet pulled. |
| ERCOT Large Load Queue | ❌ NOT USABLE | PDFs only. No project-level bulk download exists. Documented as data gap finding. |
| PJM Large Load Queue | ❌ NOT USABLE | No equivalent public dataset. Generator queue (UMD/LBL) is the available proxy. |
| MISO Large Load Queue | ❌ NOT USABLE | API blocked, no bulk download found. Same proxy approach as PJM. |

Note on the data gap: The absence of project-level large load queue data across all three target markets — during the fastest period of data center investment in history — is documented as an explicit finding. The paper argues for mandatory project-level public disclosure as a regulatory recommendation.

# Methodology

## Phase 1: Descriptive Analysis

Before any forecasting model, the paper establishes the empirical relationship between data center investment and electricity demand through descriptive evidence: regional demand growth charts, queue investment by region and year, visual co-movement, and honest documentation of the correlation vs. causation distinction.

## Phase 2: Panel Regression (Association, Not Causation)

A panel regression of regional electricity demand on lagged queue investment, with controls for temperature (HDD/CDD), regional GDP, and industrial employment. Fixed effects at the BA and time-period level. Standard errors clustered at the BA level. The resulting coefficient is interpreted as a descriptive association parameter, not a causal estimate — with explicit discussion of identification limits.

## Phase 3: Forecasting Model

The association coefficient from Phase 2 feeds a forward-looking pipeline projecting regional grid stress. Three models benchmarked: ARIMA baseline, Prophet for seasonality, XGBoost with full queue feature set. PySpark for distributed feature engineering on the full EIA hourly dataset. Output: regional grid stress forecasts by BA with uncertainty bounds.

## Phase 4: Pipeline, Dashboard, Paper & Publication

PySpark pipeline, Hex dashboard for interactive regional visualization, full NBER-style working paper submitted to SSRN, five blog posts on lambcast.net.

# Project Phases & Website Milestones

| Phase | Timeline | Core Tasks | Deliverable |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1–3 | EIA data cleaning, queue data assembly, BigQuery setup, geographic merge, descriptive visualizations | Post 1: Data sourcing writeup + exploratory charts |
| Phase 2 | Weeks 4–7 | Panel regression design, association estimate, data gap documentation, parallel trends discussion | Post 2: Methodology ¦ Post 3: Preliminary results |
| Phase 3 | Weeks 8–10 | Forecasting model build, model benchmarking, uncertainty quantification, robustness checks | Post 4: Forecasting model results |
| Phase 4 | Weeks 11–13 | PySpark pipeline, Hex dashboard, full paper draft, SSRN submission | Post 5: SSRN paper + Hex dashboard launch |

# Master Project Checklist

## Phase 1: Data Infrastructure

| # | Task | Phase | Status |
| --- | --- | --- | --- |
| 1.1 | Register for EIA API key at eia.gov/opendata | Phase 1 | ✅ Done |
| 1.2 | Pull EIA Form 930 — 184,102 rows, PJM/ERCO/MISO, 2019–2025 | Phase 1 | ✅ Done |
| 1.3 | Download UMD PJM interconnection queue dataset (2008–2024, 7,492 rows, 121 cols) | Phase 1 | ✅ Done |
| 1.4 | Load and explore LBL Queued Up 2024 dataset — 36,441 rows, 39 tabs; extract to CSV | Phase 1 | ✅ Done |
| 1.5 | Register for NOAA NCEI API key and pull daily weather data by station | Phase 1 | Not started |
| 1.6 | Download BEA regional GDP data for relevant metro areas | Phase 1 | Not started |
| 1.7 | Set up BigQuery project and load EIA + queue data | Phase 1 | Not started |
| 1.8 | Build geographic crosswalk: balancing authority to county/metro | Phase 1 | Not started |
| 1.9 | Merge electricity, queue, weather, and economic data into analysis panel | Phase 1 | Not started |
| 1.10 | Build explore_eia.py: demand trends by region, annual averages, charts (3 charts committed) | Phase 1 | ✅ Done |
| 1.10b | Build explore_queue.py: queue filings by region, cumulative GW, ERCOT by type (3 charts committed) | Phase 1 | ✅ Done |
| 1.11 | Write and publish Post 1: data sourcing writeup + exploratory charts | Phase 1 | Not started |
| 1.12 | Document the data gap: what load-side queue data does not exist and why | Phase 1 | Not started |

## Phase 2: Descriptive Analysis & Panel Regression

| # | Task | Phase | Status |
| --- | --- | --- | --- |
| 2.1 | Plot demand growth by BA over time — identify visual acceleration | Phase 2 | Not started |
| 2.2 | Plot queue investment by region and year — show investment ramp | Phase 2 | Not started |
| 2.3 | Define MW threshold for queue filings to include in regression | Phase 2 | Not started |
| 2.4 | Implement panel regression: demand on lagged queue MW + controls (Stata) | Phase 2 | Not started |
| 2.5 | Add weather (HDD/CDD) and economic controls (GDP, employment) | Phase 2 | Not started |
| 2.6 | Produce association coefficient table — clustered SEs at BA level | Phase 2 | Not started |
| 2.7 | Write data gap section: what data would enable causal ID; policy implications | Phase 2 | Not started |
| 2.8 | Write and publish Post 2: methodology writeup | Phase 2 | Not started |
| 2.9 | Write and publish Post 3: preliminary results | Phase 2 | Not started |

## Phase 3: Forecasting Model

| # | Task | Phase | Status |
| --- | --- | --- | --- |
| 3.1 | Engineer features from queue pipeline for forecasting (lagged MW, ramp rate) | Phase 3 | Not started |
| 3.2 | Build ARIMA baseline with weather + economic controls | Phase 3 | Not started |
| 3.3 | Build Prophet model — handle seasonality and holidays | Phase 3 | Not started |
| 3.4 | Build XGBoost model with full feature set from queue pipeline | Phase 3 | Not started |
| 3.5 | Benchmark all three models: RMSE, MAE, out-of-sample validation | Phase 3 | Not started |
| 3.6 | Produce regional grid stress forecasts with uncertainty bounds by BA | Phase 3 | Not started |
| 3.7 | Write and publish Post 4: forecasting model results | Phase 3 | Not started |

## Phase 4: Pipeline, Dashboard, Paper & Publication

| # | Task | Phase | Status |
| --- | --- | --- | --- |
| 4.1 | Implement PySpark pipeline for full EIA hourly dataset at scale | Phase 4 | Not started |
| 4.2 | Build Hex dashboard: regional forecast by balancing authority | Phase 4 | Not started |
| 4.3 | Write full paper draft: all sections | Phase 4 | Not started |
| 4.4 | Format paper to NBER working paper conventions | Phase 4 | Not started |
| 4.5 | Submit to SSRN as working paper; obtain citable URL | Phase 4 | Not started |
| 4.6 | Publish final PDF on lambcast.net | Phase 4 | Not started |
| 4.7 | Write and publish Post 5: SSRN submission + dashboard launch | Phase 4 | Not started |
| 4.8 | Add project to resume and LinkedIn under Applied Research Projects | Phase 4 | Not started |
| 4.9 | Email Chenyu Yang (UMD) with paper and results | Phase 4 | Not started |
| 4.10 | Send paper to Aparna Mathur (AEI) and relevant Amazon/Anthropic contacts | Phase 4 | Not started |

# Tool Stack

| Tool | Role | Notes |
| --- | --- | --- |
| Python | Core language | API pulls, data cleaning, forecasting models, PySpark. v3.12 active. |
| SQL / BigQuery | Warehouse layer | Storage and querying of the merged panel dataset at scale. |
| PySpark | Distributed compute | Feature engineering on 100M+ row EIA hourly dataset. |
| Stata | Panel regression | Association estimation, fixed effects, clustered SEs. |
| R / fixest | Optional | High-dimensional FE regressions if preferred over Stata. |
| Hex | Dashboard | Interactive regional forecast visualization. |
| Git / GitHub | Version control | All code tracked from Day 1. Branching workflow adopted going forward — work on feature branches, merge to main via pull request. |
| SSRN | Publication | Working paper submission for citable URL and academic visibility. |
| gridstatus.io | Queue data | Python library for live ISO queue data — supplement to UMD/LBL. |

# Repository Structure

| Path | Contents |
| --- | --- |
| scripts/explore_eia.py | EIA demand descriptive analysis — 3 charts: annual avg, indexed growth, monthly |
| scripts/explore_queue.py | LBNL queue descriptive analysis — 3 charts: annual GW filed, cumulative GW, ERCOT by type |
| data/eia_demand_2018_2025.csv | 184,102 rows EIA hourly demand — gitignored (regenerated by API pull) |
| data/lbnl_queue_data.csv | 36,441 rows LBNL queue data — gitignored (extracted from Excel) |
| data/pjm_main_data_for_public_with_additional_vars.csv | 7,492 rows UMD PJM queue — gitignored |
| outputs/*.png | 6 committed chart PNGs — tracked in Git for portfolio visibility |
| AI_Grid_Project_Master_v4.docx | This document — master project reference |
| AI_Grid_Project_Orientation.docx | Plain-English research logic and orientation document |
| .env | API keys — gitignored, never committed |

# Why This Project Is Strategically Distinctive

- Honest identification: explicitly documenting what can and cannot be causally identified with public data is more impressive to research-oriented readers than overclaiming

- Real data gap: the absence of project-level load queue data across PJM, ERCOT, and MISO — during the fastest period of data center investment in history — is a genuine policy finding

- Literature gap confirmed: no existing paper uses public queue data with EIA Form 930 to model and forecast data center-driven demand growth at the regional BA level

- Timely: ERCOT queue filings hit 97 GW in 2024; PJM capacity prices jumped from $30 to $330/MW-day; this is an active financial and regulatory crisis

- Dual signal: Amazon sees the pipeline and dashboard; Anthropic sees the research rigor and honest methodology

- End-to-end: raw API ingestion → panel regression → forecasting model → dashboard → published paper. Rare at graduate level

- SSRN presence: permanent citable URL, findable by researchers and hiring teams, signals work meets research standard

# Network & Outreach Targets

- Chenyu Yang, UMD Economics — co-author of UMD interconnection queue dataset; email when Phase 2 results ready; ask about updated 2024 version

- Aparna Mathur, AEI — send final paper when complete

- Amazon Applied Science recruiting — emphasize pipeline, forecasting, BigQuery, PySpark, dashboard

- Anthropic Economics team — paper + SSRN URL; emphasize honest identification and research-grade methodology

Document version 4.0  |  Updated March 2026  |  lambcast.net  |  GitHub: github.com/Lambcast/ai-infrastructure-regional-electricity-demand